## Sheet1
Appendix 2. to the Vice-chair's Report: European Region Jobs and Tasks
|  |  | EC: European Chair; VC: European Vice-Chair; EECM: European Executive Committee Member; OE: Outside Expert | ES: European Secretary; EES: European Executive Secretary
Functional Overview
1. Communication
2. Finance
3. Championships
4. Series Events
5. Laser Performance
6. Development
7. Administration
|  |  | Resposibles: A) Execution; B) Oversite | Timeline/Deadlines
Breakdown of the above structure
Communication
|  | European Circulars | A): ES & EES; B): EC & VC | Continuous
|  | Web site | A): ES & EES; B): EC & VC | Continuous
Finance
|  | LP Subsidy | A): EES; B): EC
|  | Championships | A): ES & EES; B): EC
(Host, jury, prizes, administration, bank costs)
|  | Series Events | A:) ES; B): VC
(Admin fees, prizes, honorarium)
|  | Membership Cards | A) EES B): EC
|  | Accounts: Reserves / Funds | A) EES B): EC
|  | EAGM | A): ES & EES B): EC & VC
|  | Measurement Seminar | A): ES & OE; B): EECM
|  | Office | A): EES; B) EC
| Championships |  | A): ES & EES; B): EC & EECM
|  | Bid / Selection / site visits | A): ES & EES; B): EC & EECM
|  | ILCA Rep | A): ES & EES; B): EC & EECM | at least 6 weeks before the event appointed
|  | Contract | A): ES & EES; B): EC & EECM | first draft to be sent to the host club by April 1st, final version to be signed by October 1st the year before the event
|  | Charter Boats | A): ES & EES; B): EECM
|  | Host Web site | A): ES & EES; B): EECM | partially operational by January 1st, fully oprealtional by March 1st
|  | ILCA micro-site | A): ES & EES; B): EECM | by December 1st
|  | Allocation / Entry System | A): ES & EES; B): EC | by December 1st
|  | Non-European Competitor Quota | A): ES & EES; B): EC | by December 1st
|  | NoR & SI's | A): ES, EES & OE; B): EECM | NoR by November 15th, SI by March 30
|  | Jury & Measurer | A): ES, EES & OE; B): EECM | by March 1st
|  | Prizes | A): ES & EES; B): EECM | the latest to be sent to the club: 2 weeks before the event
|  | Reporting & Photography | A): ES & EES; B): EECM | for ILCA & ISAF web pages: appointed 4 weeks before the event
|  | Scoring | A): ES, EES & OE; B): EECM | 2 weeks after each event must be available on the ILCA site
| Series Events |  | A:) ES; B): VC & EECM
|  | NoR & SI's | A:) ES & OE; B): VC & EECM | NoR by November 15th, SI by January 15th
|  | ILCA Reps | A:) ES; B): VC & EECM | Continuous
|  | Series Scoring | A:) ES & OE; B): VC & EECM | Continuous
|  | Web site | A:) ES; B): VC & EECM | by January 15th
|  | Prizes | A:) ES; B): VC & EECM | by November 15th
|  | Reporting & Photography | A:) ES; B): EECM | For "A" and "B" types Europa Cup events on-site repoters named 2 weeks before the event
|  | Questionnaire / feedback | A:) ES; B): VC & EECM | Continuous; summary evaluation for the EAGM
Laser Performance
|  | Charter boats | A): EES; B): EC
|  | Subsidy | A): EES; B): EC
|  | Other support | A): EES; B): EC
(membership cards, EAGM, series events prizes)
| Development |  | A): ES; B:) EECM | Continuous
Administration
|  | Membership Cards | A): ES & EES B): VC | by November 15th
|  | EAGM | A): ES & EES B): VC | first notice 3 months before the meeting, detailed agenda (with materials) 3 weeks before the meeting, minutes 6 weeks after meeting
|  | Measurement Seminar | A): ES & OE B): VC & EECM
|  | Youth Rankings Ladder | A): ES, EES & OE ; B): VC | Jan 1st, June 1st, Oct 1st
|  | Calendars | A): ES & EES B): VC & EECM | by October 15th
|  | Monthly job schedule and reporting | A): ES & EES B): EC & VC | monthly